## Plan
Plan ID | Plan name | Date of export
SqfegkgCvUqGh_vE_TlmgskAADNF | R26-IT-029-Electric Vehicle Management System Using Artificial Intelligence and Machine Learning | 2026-10-14

## Consolidated Data
Task ID | Task Name | Bucket | Status | Priority | Assigned To | Created By | Due date | Late | Completed Date | Completed By
l6PhGHMs-UajYSX99mFtBMkANdNL | Assign team roles | Group Formation | Completed | Important | FERNANDO C.T.H.H.D it22247490;JAYARATHNE WTDK it22071170;DIAS N.T.B.P it22134080;VIDUSHAN A A D N it22157928 | FERNANDO C.T.H.H.D it22247490 | 2025-10-22 | false | 2026-08-26 | FERNANDO C.T.H.H.D it22247490
FkS0p3dd5kq8_v_i16cEJckAKDK3 | Conduct initial meeting | Group Formation | Completed | Medium | FERNANDO C.T.H.H.D it22247490;JAYARATHNE WTDK it22071170;DIAS N.T.B.P it22134080;VIDUSHAN A A D N it22157928 | FERNANDO C.T.H.H.D it22247490 | 2025-10-22 | false | 2026-10-14 | VIDUSHAN A A D N it22157928
q5xU3SQC8EGsTMsaiP2r38kAO_u9 | Submit the research group form | Group Formation | Completed | Urgent | VIDUSHAN A A D N it22157928 | FERNANDO C.T.H.H.D it22247490 | 2025-10-25 | false | 2026-10-14 | VIDUSHAN A A D N it22157928
qjbP4CkTEUuUcU1QhxrH2skAKhn8 | Get initial approval | Group Formation | Completed | Important | FERNANDO C.T.H.H.D it22247490;JAYARATHNE WTDK it22071170;DIAS N.T.B.P it22134080;VIDUSHAN A A D N it22157928 | FERNANDO C.T.H.H.D it22247490 | 2025-11-18 | false | 2026-10-14 | FERNANDO C.T.H.H.D it22247490
NhCPvUnmO0ORNkNmArFTvMkAElQ_ | Review current EV management problems and user pain points | Topic Selection & Problem Identification | Completed | Important | FERNANDO C.T.H.H.D it22247490;JAYARATHNE WTDK it22071170;DIAS N.T.B.P it22134080;VIDUSHAN A A D N it22157928 | FERNANDO C.T.H.H.D it22247490 |  | false | 2026-08-28 | FERNANDO C.T.H.H.D it22247490
GGo-22naPEGflUn4TYZoGskAN_ry | Define the main research problem | Topic Selection & Problem Identification | Completed | Urgent | FERNANDO C.T.H.H.D it22247490;JAYARATHNE WTDK it22071170;DIAS N.T.B.P it22134080;VIDUSHAN A A D N it22157928 | FERNANDO C.T.H.H.D it22247490 |  | false | 2026-08-28 | FERNANDO C.T.H.H.D it22247490
DhVL37Q8aEe17sFtXwE5C8kAChrH | Identify four independent novelty components | Topic Selection & Problem Identification | Completed | Important | FERNANDO C.T.H.H.D it22247490;JAYARATHNE WTDK it22071170;DIAS N.T.B.P it22134080;VIDUSHAN A A D N it22157928 | FERNANDO C.T.H.H.D it22247490 |  | false | 2026-08-28 | FERNANDO C.T.H.H.D it22247490
kUvROvBMzU21U-MCxDvGJskAIOCx | Component 1 – EV Operational Anomaly Detection | Topic Selection & Problem Identification | Completed | Urgent | VIDUSHAN A A D N it22157928 | FERNANDO C.T.H.H.D it22247490 |  | false | 2026-08-30 | VIDUSHAN A A D N it22157928
pvfOojKHNEOMQOjAdbnJbskAD4mS | Component 2 – Adaptive Battery Health Prediction | Topic Selection & Problem Identification | Completed | Important | FERNANDO C.T.H.H.D it22247490 | FERNANDO C.T.H.H.D it22247490 |  | false | 2026-08-28 | FERNANDO C.T.H.H.D it22247490
B4JBxzpOBU-ucKhMBXqxnMkAILmo | Component 3 – Charging Optimization & Range Prediction | Topic Selection & Problem Identification | Completed | Important | DIAS N.T.B.P it22134080 | FERNANDO C.T.H.H.D it22247490 |  | false | 2026-08-31 | DIAS N.T.B.P it22134080
53gKv62QH0WbeknsGKCrLskAACp6 | Prepare initial problem statement and research justification | TAF Preparation & Supervisor Approval | Completed | Important | FERNANDO C.T.H.H.D it22247490;JAYARATHNE WTDK it22071170;DIAS N.T.B.P it22134080;VIDUSHAN A A D N it22157928 | FERNANDO C.T.H.H.D it22247490 |  | false | 2026-08-28 | FERNANDO C.T.H.H.D it22247490
bF6OlCkxbEmynNxZgGfekckAMoHB | Prepare novelty and research-gap summary | TAF Preparation & Supervisor Approval | Completed | Important | FERNANDO C.T.H.H.D it22247490;JAYARATHNE WTDK it22071170;DIAS N.T.B.P it22134080;VIDUSHAN A A D N it22157928 | FERNANDO C.T.H.H.D it22247490 |  | false | 2026-08-28 | FERNANDO C.T.H.H.D it22247490
Z-SrjetcP0KQ6La0nQsEKckAMplh | Prepare TAF / topic approval document | TAF Preparation & Supervisor Approval | Completed | Urgent | FERNANDO C.T.H.H.D it22247490;JAYARATHNE WTDK it22071170;DIAS N.T.B.P it22134080;VIDUSHAN A A D N it22157928 | FERNANDO C.T.H.H.D it22247490 |  | false | 2026-08-28 | FERNANDO C.T.H.H.D it22247490
dUw29kygJEmeihlSjZSjvMkAKr7R | Submit TAF and attend evaluation | TAF Preparation & Supervisor Approval | Completed | Urgent | FERNANDO C.T.H.H.D it22247490;JAYARATHNE WTDK it22071170;DIAS N.T.B.P it22134080;VIDUSHAN A A D N it22157928 | FERNANDO C.T.H.H.D it22247490 |  | false | 2026-08-28 | FERNANDO C.T.H.H.D it22247490
IAVc8NaQ_EGw-Z_3bF34KMkAK84z | Draft charter | Project Charter Development | Completed | Medium | FERNANDO C.T.H.H.D it22247490;JAYARATHNE WTDK it22071170;DIAS N.T.B.P it22134080;VIDUSHAN A A D N it22157928 | FERNANDO C.T.H.H.D it22247490 |  | false | 2026-08-28 | FERNANDO C.T.H.H.D it22247490
meL2Qp1T8kGedA76m0mEwskAPqbE | Prepare timeline | Project Charter Development | Completed | Medium | FERNANDO C.T.H.H.D it22247490;JAYARATHNE WTDK it22071170;DIAS N.T.B.P it22134080;VIDUSHAN A A D N it22157928 | FERNANDO C.T.H.H.D it22247490 |  | false | 2026-08-28 | FERNANDO C.T.H.H.D it22247490
vbO3MCqHdUGeehL_f_-mgMkALcQy | Submit charter | Project Charter Development | Completed | Medium | VIDUSHAN A A D N it22157928 | FERNANDO C.T.H.H.D it22247490 |  | false | 2026-08-30 | VIDUSHAN A A D N it22157928
6qe8JmjeOU-XJZJnODWwTckAH7tg | Prepare Proposal – EV Operational Anomaly Detection | Project Proposal Document Preparation & CDAP Submission | Completed | Medium | VIDUSHAN A A D N it22157928 | FERNANDO C.T.H.H.D it22247490 |  | false | 2026-08-30 | VIDUSHAN A A D N it22157928
Qu23s96xN0eMwZIZENcY9ckAK7Cn | Prepare Proposal – Adaptive Battery Health Prediction and Personalized Recommendation | Project Proposal Document Preparation & CDAP Submission | Completed | Medium | FERNANDO C.T.H.H.D it22247490 | FERNANDO C.T.H.H.D it22247490 |  | false | 2026-08-28 | FERNANDO C.T.H.H.D it22247490
RsW4E0RjeEKYrlsmvmz9LskAJyIe | Prepare Proposal – Charging Optimization & Range Prediction | Project Proposal Document Preparation & CDAP Submission | Completed | Medium | DIAS N.T.B.P it22134080 | FERNANDO C.T.H.H.D it22247490 |  | false | 2026-08-31 | DIAS N.T.B.P it22134080
ie1_3JqkTESJIc7yJurOKskAIv_0 | Prepare Proposal –AI-Based EV Virtual Assistant | Project Proposal Document Preparation & CDAP Submission | Completed | Medium | JAYARATHNE WTDK it22071170 | FERNANDO C.T.H.H.D it22247490 |  | false | 2026-08-30 | VIDUSHAN A A D N it22157928
Vf7ge5kitEyohldjce9DmMkAI4Tv | Upload Individual Proposal Documents to CDAP Cloud Storage | Project Proposal Document Preparation & CDAP Submission | Completed | Urgent | FERNANDO C.T.H.H.D it22247490;JAYARATHNE WTDK it22071170;DIAS N.T.B.P it22134080;VIDUSHAN A A D N it22157928 | FERNANDO C.T.H.H.D it22247490 | 2026-03-16 | false | 2026-08-28 | FERNANDO C.T.H.H.D it22247490
JmjqSqSoyEyxvN4ab00OHMkAO0qK | Prepare Presentation Slides | Proposal Presentation 1 | Completed | Important | FERNANDO C.T.H.H.D it22247490;JAYARATHNE WTDK it22071170;DIAS N.T.B.P it22134080;VIDUSHAN A A D N it22157928 | FERNANDO C.T.H.H.D it22247490 |  | false | 2026-08-28 | FERNANDO C.T.H.H.D it22247490
bKQ_pi7J9UufCJ1ib4taHckAPC61 | Finalize Proposal Presentation Slides | Proposal Presentation 1 | Completed | Important | FERNANDO C.T.H.H.D it22247490;JAYARATHNE WTDK it22071170;DIAS N.T.B.P it22134080;VIDUSHAN A A D N it22157928 | FERNANDO C.T.H.H.D it22247490 |  | false | 2026-08-28 | FERNANDO C.T.H.H.D it22247490
QcPABT1Y5kyZ5YqYAAV0iMkAPvi9 | Meet with Supervisor Before Proposal Presentation | Proposal Presentation 1 | Completed | Medium | FERNANDO C.T.H.H.D it22247490;JAYARATHNE WTDK it22071170;DIAS N.T.B.P it22134080;VIDUSHAN A A D N it22157928 | FERNANDO C.T.H.H.D it22247490 |  | false | 2026-08-28 | FERNANDO C.T.H.H.D it22247490
MydYu4aCy0OY-1sHI2c6QskAN0Fq | Conduct Proposal Presentation to Panel | Proposal Presentation 1 | Completed | Important | FERNANDO C.T.H.H.D it22247490;JAYARATHNE WTDK it22071170;DIAS N.T.B.P it22134080;VIDUSHAN A A D N it22157928 | FERNANDO C.T.H.H.D it22247490 | 2026-03-16 | false | 2026-08-28 | FERNANDO C.T.H.H.D it22247490
DdiZ1bU8Uk-3C-5jXMEHN8kAJgfU | Finalize research topic title - Electric Vehicle Management System Using Artificial Intelligence and Machine Learning | Find Research Topic & Supervisor | Completed | Important | FERNANDO C.T.H.H.D it22247490;JAYARATHNE WTDK it22071170;DIAS N.T.B.P it22134080;VIDUSHAN A A D N it22157928 | FERNANDO C.T.H.H.D it22247490 |  | false | 2026-08-28 | FERNANDO C.T.H.H.D it22247490
fPKUCnrCwEy7Lb2FPzijdMkAAWhX | Found supervisor and co supervisor | Find Research Topic & Supervisor | Completed | Urgent | FERNANDO C.T.H.H.D it22247490;JAYARATHNE WTDK it22071170;DIAS N.T.B.P it22134080;VIDUSHAN A A D N it22157928 | FERNANDO C.T.H.H.D it22247490 |  | false | 2026-08-28 | FERNANDO C.T.H.H.D it22247490
X755i-7ZDkinbUm7g5f48skAGOLa | Component 4 - Finalize Predictive Charging & Breakdown Assistance System | Topic Selection & Problem Identification | Completed | Important | JAYARATHNE WTDK it22071170 | JAYARATHNE WTDK it22071170 |  | false | 2026-08-30 | JAYARATHNE WTDK it22071170
WXTvBOVYVUyV6uN4PL2pN8kAL5FD | Discuss topic ideas with supervisor | Group Formation | Completed | Important | FERNANDO C.T.H.H.D it22247490;JAYARATHNE WTDK it22071170;DIAS N.T.B.P it22134080;VIDUSHAN A A D N it22157928 | JAYARATHNE WTDK it22071170 |  | false | 2026-10-14 | FERNANDO C.T.H.H.D it22247490
uyc087d95Em6LqUqOf7NeskAObO5 | Review related research papers and Identify contradictions or gaps | TAF Preparation & Supervisor Approval | Completed | Important | JAYARATHNE WTDK it22071170 | JAYARATHNE WTDK it22071170 |  | false | 2026-08-30 | JAYARATHNE WTDK it22071170
uuS0K5KkEUaz3lXY1b-_vskAJBB7 | Create GitHub Repository | Check List -1 Development | Completed | Important | VIDUSHAN A A D N it22157928 | FERNANDO C.T.H.H.D it22247490 | 2026-03-10 | false | 2026-10-14 | VIDUSHAN A A D N it22157928
Qrz89X7DVkuEb8ZZ71zT0ckAOdgX | Define Repository Structure & Folder Organization | Check List -1 Development | Completed | Medium | VIDUSHAN A A D N it22157928 | FERNANDO C.T.H.H.D it22247490 | 2026-05-13 | false | 2026-10-14 | VIDUSHAN A A D N it22157928
dGjzrpftg0GXpX_4DflWI8kAJTG9 | Create Feature Branches for Individual Components | Check List -1 Development | Completed | Medium | FERNANDO C.T.H.H.D it22247490;JAYARATHNE WTDK it22071170;DIAS N.T.B.P it22134080;VIDUSHAN A A D N it22157928 | FERNANDO C.T.H.H.D it22247490 |  | false | 2026-10-14 | FERNANDO C.T.H.H.D it22247490
4LqW2QJxx0W2o23dksLdrMkAGhUL | Update README File with Project Overview & Architecture | Check List -1 Development | Completed | Medium | FERNANDO C.T.H.H.D it22247490;JAYARATHNE WTDK it22071170;DIAS N.T.B.P it22134080;VIDUSHAN A A D N it22157928 | FERNANDO C.T.H.H.D it22247490 |  | false | 2026-10-14 | FERNANDO C.T.H.H.D it22247490
a61Cq1VmBUSHf-Nyspur7skAG4qt | Develop Individual Component for PP 1 (AI-Based EV Operational Anomaly Detection) | Individual Module Development | Completed | Medium | VIDUSHAN A A D N it22157928 | FERNANDO C.T.H.H.D it22247490 | 2026-05-11 | false | 2026-10-14 | VIDUSHAN A A D N it22157928
LEzonIOlqEWu1Dls3uCfV8kADF0z | Develop Individual Component for PP 1 (Adaptive Battery Health Prediction and Personalized Recommendation) | Individual Module Development | Completed | Medium | FERNANDO C.T.H.H.D it22247490 | FERNANDO C.T.H.H.D it22247490 |  | false | 2026-10-14 | FERNANDO C.T.H.H.D it22247490
DoXNsegPSkS56j9fsmXPK8kAFz5T | Develop Individual Component for PP 1 (Intelligent EV Charging Optimization and Range Prediction) | Individual Module Development | Completed | Medium | DIAS N.T.B.P it22134080 | FERNANDO C.T.H.H.D it22247490 |  | false | 2026-10-14 | DIAS N.T.B.P it22134080
itsHdCjSAUK3vwimNeRd8skACJS7 | Develop Individual Component for PP 1 (AI-Based EV Virtual Assistant) | Individual Module Development | Completed | Medium | JAYARATHNE WTDK it22071170 | FERNANDO C.T.H.H.D it22247490 |  | false | 2026-10-14 | FERNANDO C.T.H.H.D it22247490
nLD4fCg1302n2k0aXOZKFMkAKiqN | Prepare individual module slides | Progress Presentation 1 (PP1) | Completed | Medium | FERNANDO C.T.H.H.D it22247490;JAYARATHNE WTDK it22071170;DIAS N.T.B.P it22134080;VIDUSHAN A A D N it22157928 | FERNANDO C.T.H.H.D it22247490 |  | false | 2026-10-14 | FERNANDO C.T.H.H.D it22247490
vfnIt8-YEES4DXoiK9SLgMkAJFo7 | Finalize Progress Presentation 1 Slides | Progress Presentation 1 (PP1) | Completed | Medium | FERNANDO C.T.H.H.D it22247490 | FERNANDO C.T.H.H.D it22247490 |  | false | 2026-10-14 | FERNANDO C.T.H.H.D it22247490
iyEPWiQ_4kmNMMI5fkGsickAKzhk | Meet with Supervisor Before Progress Presentation 1 | Progress Presentation 1 (PP1) | Completed | Medium | FERNANDO C.T.H.H.D it22247490;JAYARATHNE WTDK it22071170;DIAS N.T.B.P it22134080;VIDUSHAN A A D N it22157928 | FERNANDO C.T.H.H.D it22247490 |  | false | 2026-10-14 | FERNANDO C.T.H.H.D it22247490
SjawLahGFkOrU7GyqVTjeckAKiGp | Prepare Speaking Notes | Progress Presentation 1 (PP1) | Completed | Medium | FERNANDO C.T.H.H.D it22247490;JAYARATHNE WTDK it22071170;DIAS N.T.B.P it22134080;VIDUSHAN A A D N it22157928 | FERNANDO C.T.H.H.D it22247490 |  | false | 2026-10-14 | FERNANDO C.T.H.H.D it22247490
g9M9qOkl7kukkdKEFggZH8kAKUjS | Conduct Progress Presentation 1 to Panel | Progress Presentation 1 (PP1) | Completed | Important | FERNANDO C.T.H.H.D it22247490;JAYARATHNE WTDK it22071170;DIAS N.T.B.P it22134080 | FERNANDO C.T.H.H.D it22247490 | 2026-05-11 | false | 2026-10-14 | FERNANDO C.T.H.H.D it22247490
ZEakAIhS80mVrJR0b5s_IMkADWzR | Submit Progress Presentation 1 (PP1) | Progress Presentation 1 (PP1) | Completed | Medium | VIDUSHAN A A D N it22157928 | FERNANDO C.T.H.H.D it22247490 | 2026-05-11 | false | 2026-10-14 | VIDUSHAN A A D N it22157928
AzDP16qFdEq5fOxs0wS_1MkAEQm_ | Review Immediate Verbal Feedback from PP1 | Progress Presentation 2 (PP2) – Integration & Improvement Phase | Completed | Medium | FERNANDO C.T.H.H.D it22247490;JAYARATHNE WTDK it22071170;DIAS N.T.B.P it22134080;VIDUSHAN A A D N it22157928 | FERNANDO C.T.H.H.D it22247490 |  | false | 2026-10-14 | FERNANDO C.T.H.H.D it22247490
dWW7kGW46EW1IeWkRaeBy8kAKUE6 | Discuss Official Panel Comments with Supervisor | Progress Presentation 2 (PP2) – Integration & Improvement Phase | Completed | Medium | FERNANDO C.T.H.H.D it22247490;JAYARATHNE WTDK it22071170;DIAS N.T.B.P it22134080;VIDUSHAN A A D N it22157928 | FERNANDO C.T.H.H.D it22247490 |  | false | 2026-10-14 | FERNANDO C.T.H.H.D it22247490
_si6_ku4Y0qWBvV_pAwn38kANW7d | Implement Initial Improvements Based on Verbal Feedback | Progress Presentation 2 (PP2) – Integration & Improvement Phase | Completed | Medium | FERNANDO C.T.H.H.D it22247490;JAYARATHNE WTDK it22071170;DIAS N.T.B.P it22134080;VIDUSHAN A A D N it22157928 | FERNANDO C.T.H.H.D it22247490 |  | false | 2026-10-14 | FERNANDO C.T.H.H.D it22247490
LcsutcMT4Em85i-sRSkfH8kAE6Ri | Receive & Review Official Panel Comments (Written) | Progress Presentation 2 (PP2) – Integration & Improvement Phase | Completed | Medium | FERNANDO C.T.H.H.D it22247490;JAYARATHNE WTDK it22071170;DIAS N.T.B.P it22134080;VIDUSHAN A A D N it22157928 | FERNANDO C.T.H.H.D it22247490 |  | false | 2026-10-14 | FERNANDO C.T.H.H.D it22247490
h4e-K5MruUORaTQdyXisnskABVO3 | Implement Improvements Based on Official panel Comments | Progress Presentation 2 (PP2) – Integration & Improvement Phase | Completed | Medium | FERNANDO C.T.H.H.D it22247490;JAYARATHNE WTDK it22071170;DIAS N.T.B.P it22134080;VIDUSHAN A A D N it22157928 | FERNANDO C.T.H.H.D it22247490 |  | false | 2026-10-14 | FERNANDO C.T.H.H.D it22247490
V8DmFE4dc0ep-Yix1AAOaskAJ9dP | System Integration – Combine All Modules | Progress Presentation 2 (PP2) – Integration & Improvement Phase | Completed | Medium | FERNANDO C.T.H.H.D it22247490;JAYARATHNE WTDK it22071170;DIAS N.T.B.P it22134080;VIDUSHAN A A D N it22157928 | FERNANDO C.T.H.H.D it22247490 |  | false | 2026-10-14 | FERNANDO C.T.H.H.D it22247490
7GLeNHnr9UWr6uvAhKqt0MkAIzML | Prepare Checklist 2 – MS Planner Management Review | Progress Presentation 2 (PP2) – Integration & Improvement Phase | Completed | Medium | FERNANDO C.T.H.H.D it22247490 | FERNANDO C.T.H.H.D it22247490 |  | false | 2026-10-14 | FERNANDO C.T.H.H.D it22247490
xtPCw0_IRkaQbFo5aa3KcckAJi0c | Finalize Progress Presentation 2 Slides | Progress Presentation 2 (PP2) – Integration & Improvement Phase | Completed | Medium | FERNANDO C.T.H.H.D it22247490;JAYARATHNE WTDK it22071170;DIAS N.T.B.P it22134080;VIDUSHAN A A D N it22157928 | FERNANDO C.T.H.H.D it22247490 |  | false | 2026-10-14 | FERNANDO C.T.H.H.D it22247490
MfcYyM30Z06a7qMYo35zVMkAItei | Meet with Supervisor Before Progress Presentation 2 | Progress Presentation 2 (PP2) – Integration & Improvement Phase | Completed | Medium | FERNANDO C.T.H.H.D it22247490;JAYARATHNE WTDK it22071170;DIAS N.T.B.P it22134080;VIDUSHAN A A D N it22157928 | FERNANDO C.T.H.H.D it22247490 |  | false | 2026-10-14 | FERNANDO C.T.H.H.D it22247490
T4XoDKZGn0KP4n_2S42nuskAOnAC | Prepare Speaking Notes | Progress Presentation 2 (PP2) – Integration & Improvement Phase | Completed | Medium | FERNANDO C.T.H.H.D it22247490;JAYARATHNE WTDK it22071170;DIAS N.T.B.P it22134080;VIDUSHAN A A D N it22157928 | FERNANDO C.T.H.H.D it22247490 |  | false | 2026-10-14 | FERNANDO C.T.H.H.D it22247490
lq4EnTedGki5Gntm_hK3h8kAPGoJ | Conduct Progress Presentation 2 to Panel | Progress Presentation 2 (PP2) – Integration & Improvement Phase | Completed | Medium | FERNANDO C.T.H.H.D it22247490;JAYARATHNE WTDK it22071170;DIAS N.T.B.P it22134080;VIDUSHAN A A D N it22157928 | FERNANDO C.T.H.H.D it22247490 | 2026-08-31 | false | 2026-10-14 | FERNANDO C.T.H.H.D it22247490
-WYrHYoVBEKHsloqiYl5VckAOfSw | Submit Progress Presentation 2 (PP2) | Progress Presentation 2 (PP2) – Integration & Improvement Phase | Completed | Medium | VIDUSHAN A A D N it22157928 | FERNANDO C.T.H.H.D it22247490 | 2026-08-31 | false | 2026-10-14 | VIDUSHAN A A D N it22157928
6hXYPp0nk0q_qFWO4yq448kANVgt | Individual draft thesis ready | Draft Thesis Submission | Completed | Medium | FERNANDO C.T.H.H.D it22247490;JAYARATHNE WTDK it22071170;DIAS N.T.B.P it22134080;VIDUSHAN A A D N it22157928 | FERNANDO C.T.H.H.D it22247490 |  | false | 2026-10-14 | FERNANDO C.T.H.H.D it22247490
LvmdEYb0zE-vG_lIkameJ8kALdax | Group draft thesis ready | Draft Thesis Submission | Completed | Medium | FERNANDO C.T.H.H.D it22247490;JAYARATHNE WTDK it22071170;DIAS N.T.B.P it22134080 | FERNANDO C.T.H.H.D it22247490 |  | false | 2026-10-14 | FERNANDO C.T.H.H.D it22247490
pbORX9eSSUK_I4vYamiY98kAK1Uu | Individual draft thesis submit | Draft Thesis Submission | Completed | Important | FERNANDO C.T.H.H.D it22247490;JAYARATHNE WTDK it22071170;DIAS N.T.B.P it22134080;VIDUSHAN A A D N it22157928 | FERNANDO C.T.H.H.D it22247490 | 2026-10-11 | false | 2026-10-14 | FERNANDO C.T.H.H.D it22247490
Xu3clPnLxUmkXYzxYP5m98kAA7Ma | Group draft thesis submit | Draft Thesis Submission | Completed | Important | VIDUSHAN A A D N it22157928 | FERNANDO C.T.H.H.D it22247490 | 2026-10-11 | false | 2026-10-14 | VIDUSHAN A A D N it22157928
RKVFew04_Eq8KoHOGh_KqMkAGJcJ | Create and initialize repository | Website Submission | Completed | Medium | FERNANDO C.T.H.H.D it22247490 | FERNANDO C.T.H.H.D it22247490 |  | false | 2026-10-14 | FERNANDO C.T.H.H.D it22247490
VUB4vD3FfUGytZueX3YM9MkAHGzS | Requirements analysis for create website | Website Submission | Completed | Medium | FERNANDO C.T.H.H.D it22247490 | FERNANDO C.T.H.H.D it22247490 |  | false | 2026-10-14 | FERNANDO C.T.H.H.D it22247490
LUTOMLEfNkiPwiQz4NdVbckALglR | Deploy website | Website Submission | Completed | Medium | FERNANDO C.T.H.H.D it22247490 | FERNANDO C.T.H.H.D it22247490 |  | false | 2026-10-14 | FERNANDO C.T.H.H.D it22247490
D2QbxjMCqEGkZeaBr8nEEskAKmZQ | UI modifications complete | Website Submission | Completed | Medium | FERNANDO C.T.H.H.D it22247490 | FERNANDO C.T.H.H.D it22247490 |  | false | 2026-10-14 | FERNANDO C.T.H.H.D it22247490
vVhm2Aj3fUmS585yXeTZrskAN_E1 | Prepare and submit link | Website Submission | Completed | Important | VIDUSHAN A A D N it22157928 | FERNANDO C.T.H.H.D it22247490 | 2026-10-11 | false | 2026-10-14 | VIDUSHAN A A D N it22157928
RBF5ztKfw024ixmpzXOOpskAFm4o | Start to create MS Planner | Final Checklist Submission | Completed | Medium | FERNANDO C.T.H.H.D it22247490 | FERNANDO C.T.H.H.D it22247490 |  | false | 2026-10-14 | FERNANDO C.T.H.H.D it22247490
JgLqytPG7U6T9uZEmG5mM8kAAdlq | Update task status (Completed / In Progress) | Final Checklist Submission | Completed | Medium | FERNANDO C.T.H.H.D it22247490;JAYARATHNE WTDK it22071170;DIAS N.T.B.P it22134080;VIDUSHAN A A D N it22157928 | FERNANDO C.T.H.H.D it22247490 |  | false | 2026-10-14 | FERNANDO C.T.H.H.D it22247490
UbZ1ktDMRkCt9sg_X2ceXckAOzqo | Check due dates are set | Final Checklist Submission | Completed | Medium | FERNANDO C.T.H.H.D it22247490 | FERNANDO C.T.H.H.D it22247490 |  | false | 2026-10-14 | FERNANDO C.T.H.H.D it22247490
W5oHL6afAUW9YdODjGsCc8kAKH2_ | Review all Planner tasks | Final Checklist Submission | Completed | Medium | FERNANDO C.T.H.H.D it22247490 | FERNANDO C.T.H.H.D it22247490 |  | false | 2026-10-14 | FERNANDO C.T.H.H.D it22247490
UOFxpcBi1kuTcbHsuHLPlckAAENS | Submit the checklist | Final Checklist Submission | Completed | Important | VIDUSHAN A A D N it22157928 | FERNANDO C.T.H.H.D it22247490 | 2026-10-14 | false | 2026-10-14 | VIDUSHAN A A D N it22157928
A-IqtnChEU-_7tiUMBluW8kANb0f | Finalize research app | Final Presentation and Viva | Not started | Medium | FERNANDO C.T.H.H.D it22247490;JAYARATHNE WTDK it22071170;DIAS N.T.B.P it22134080;VIDUSHAN A A D N it22157928 | FERNANDO C.T.H.H.D it22247490 | 2026-10-18 | false
LwnswY1Y20qputvjoEP74MkANvI8 | Prepare presentation slides | Final Presentation and Viva | Not started | Medium | FERNANDO C.T.H.H.D it22247490;JAYARATHNE WTDK it22071170;DIAS N.T.B.P it22134080;VIDUSHAN A A D N it22157928 | FERNANDO C.T.H.H.D it22247490 |  | false
Zxd2eM5oX0a1F75qPMi8K8kANoIE | Practice presentation | Final Presentation and Viva | Not started | Medium | DIAS N.T.B.P it22134080;FERNANDO C.T.H.H.D it22247490;JAYARATHNE WTDK it22071170;VIDUSHAN A A D N it22157928 | FERNANDO C.T.H.H.D it22247490 |  | false
PExXJ9Vwkku1sjlh2hmQTskAPW0K | Prepare for questions (Q&A) | Final Presentation and Viva | Not started | Medium | FERNANDO C.T.H.H.D it22247490;JAYARATHNE WTDK it22071170;DIAS N.T.B.P it22134080;VIDUSHAN A A D N it22157928 | FERNANDO C.T.H.H.D it22247490 |  | false
Q3l1YE2BrUedxYfo_LWAXckAE8gV | Deliver presentation and attend viva | Final Presentation and Viva | Not started | Important | FERNANDO C.T.H.H.D it22247490;JAYARATHNE WTDK it22071170;DIAS N.T.B.P it22134080;VIDUSHAN A A D N it22157928 | FERNANDO C.T.H.H.D it22247490 | 2026-10-19 | false
IcIbwH2q7kqHAT6nv7KbEMkAA2_a | Identify Research Gaps & Define Theoretical FoundationIdentify Research Gaps & Define Theoretical Foundation | Research Paper Review & Background Study | Not started | Medium | DIAS N.T.B.P it22134080;FERNANDO C.T.H.H.D it22247490;JAYARATHNE WTDK it22071170;VIDUSHAN A A D N it22157928 | FERNANDO C.T.H.H.D it22247490 |  | false
DeZWmIH4YkWCra9skHyTEMkABZoD | Consolidate Literature Findings & Prepare Background Summary | Research Paper Review & Background Study | Not started | Medium | DIAS N.T.B.P it22134080;FERNANDO C.T.H.H.D it22247490;JAYARATHNE WTDK it22071170;VIDUSHAN A A D N it22157928 | FERNANDO C.T.H.H.D it22247490 |  | false
TgrWE88CSk6lYB6Wgu1XGMkADp7R | Conduct Individual Literature Review for All Components | Research Paper Review & Background Study | Not started | Medium | FERNANDO C.T.H.H.D it22247490;JAYARATHNE WTDK it22071170;DIAS N.T.B.P it22134080;VIDUSHAN A A D N it22157928 | FERNANDO C.T.H.H.D it22247490 |  | false
Kz8FR7qRLEOjvi-Vbw9iockADjpG | Collect references / journals | Research Paper Submission | Not started | Medium | DIAS N.T.B.P it22134080;FERNANDO C.T.H.H.D it22247490;JAYARATHNE WTDK it22071170;VIDUSHAN A A D N it22157928 | FERNANDO C.T.H.H.D it22247490 |  | false
bhlgVd7xukmqbQ2GbojVB8kAEy28 | Start to write the research paper | Research Paper Submission | Not started | Medium | FERNANDO C.T.H.H.D it22247490;JAYARATHNE WTDK it22071170;DIAS N.T.B.P it22134080;VIDUSHAN A A D N it22157928 | FERNANDO C.T.H.H.D it22247490 |  | false
iygpwsyuik2ikzDh2EEZQ8kAHocz | Edit formatting & citations | Research Paper Submission | Not started | Medium | DIAS N.T.B.P it22134080;FERNANDO C.T.H.H.D it22247490;JAYARATHNE WTDK it22071170;VIDUSHAN A A D N it22157928 | FERNANDO C.T.H.H.D it22247490 |  | false
tud9R25JvU2e5goYtOz7TMkAGZre | Final proofread & submit the research paper | Research Paper Submission | Not started | Important | VIDUSHAN A A D N it22157928 | FERNANDO C.T.H.H.D it22247490 | 2026-10-23 | false
89xEbynrU0OVPNVlaQFRAckAB_Vh | Individual final thesis ready | Final Thesis Submission | Not started | Medium | FERNANDO C.T.H.H.D it22247490;JAYARATHNE WTDK it22071170;DIAS N.T.B.P it22134080;VIDUSHAN A A D N it22157928 | FERNANDO C.T.H.H.D it22247490 |  | false
pOsKe4duI0iF_u_xza7hXskAHu2S | Group final thesis ready | Final Thesis Submission | Not started | Medium | FERNANDO C.T.H.H.D it22247490;JAYARATHNE WTDK it22071170;DIAS N.T.B.P it22134080;VIDUSHAN A A D N it22157928 | FERNANDO C.T.H.H.D it22247490 |  | false
AjYrkQ6KHkaKQ0V_oMqzaskAEsqu | Individual final thesis submitted | Final Thesis Submission | Not started | Medium | FERNANDO C.T.H.H.D it22247490;JAYARATHNE WTDK it22071170;DIAS N.T.B.P it22134080;VIDUSHAN A A D N it22157928 | FERNANDO C.T.H.H.D it22247490 | 2026-10-28 | false
JLvNuUfCkk6JuhyKsRRBTMkANrNe | Group final thesis submit | Final Thesis Submission | Not started | Important | VIDUSHAN A A D N it22157928 | FERNANDO C.T.H.H.D it22247490 | 2026-10-28 | false
7M5tOKJtlkWEMFB9sQpBr8kAIFGy | Review logbook for completeness | Logbook Submission | Not started | Medium | FERNANDO C.T.H.H.D it22247490;JAYARATHNE WTDK it22071170;DIAS N.T.B.P it22134080;VIDUSHAN A A D N it22157928 | FERNANDO C.T.H.H.D it22247490 |  | false
2fICRyrZ2kSxZPpZqocZtckANgWj | Ensure all days are recorded | Logbook Submission | Not started | Medium | FERNANDO C.T.H.H.D it22247490;JAYARATHNE WTDK it22071170;DIAS N.T.B.P it22134080;VIDUSHAN A A D N it22157928 | FERNANDO C.T.H.H.D it22247490 |  | false
_geVoGLiuEaY2Ur5GzvdBMkACxzK | Get supervisor signature for all days | Logbook Submission | Not started | Medium | FERNANDO C.T.H.H.D it22247490;JAYARATHNE WTDK it22071170;DIAS N.T.B.P it22134080;VIDUSHAN A A D N it22157928 | FERNANDO C.T.H.H.D it22247490 |  | false
z0qvHIkOmUCEFld9bwdXBskAB2vh | Submit logbook | Logbook Submission | Not started | Important | FERNANDO C.T.H.H.D it22247490;JAYARATHNE WTDK it22071170;DIAS N.T.B.P it22134080;VIDUSHAN A A D N it22157928 | FERNANDO C.T.H.H.D it22247490 | 2026-10-21 | false
ZYDXiZ_TNE2ITz9dXa5OOskAN_0C | Prepare paper revision/publication follow-up plan | Research Paper publication evidence submission | Not started | Medium | FERNANDO C.T.H.H.D it22247490;JAYARATHNE WTDK it22071170;DIAS N.T.B.P it22134080;VIDUSHAN A A D N it22157928 | FERNANDO C.T.H.H.D it22247490 |  | false
031uK-lxfEa8elCOWGsMaMkAAHMR | Respond to reviewer/editor feedback if received | Research Paper publication evidence submission | Not started | Medium | FERNANDO C.T.H.H.D it22247490;JAYARATHNE WTDK it22071170;DIAS N.T.B.P it22134080;VIDUSHAN A A D N it22157928 | FERNANDO C.T.H.H.D it22247490 |  | false
WwbjiQ9rP0-E3kyoQHfXZckADP6O | Collect publication/acceptance evidence | Research Paper publication evidence submission | Not started | Medium | FERNANDO C.T.H.H.D it22247490;JAYARATHNE WTDK it22071170;DIAS N.T.B.P it22134080;VIDUSHAN A A D N it22157928 | FERNANDO C.T.H.H.D it22247490 |  | false
svcLURukxU6mrDKaKkRJB8kABbB4 | Research Paper publication evidence submission | Research Paper publication evidence submission | Not started | Medium | VIDUSHAN A A D N it22157928 | FERNANDO C.T.H.H.D it22247490 | 2026-12-01 | false

## Tasks
Task ID | Task Name | Bucket | Goal | Status | Priority | Assigned To | Created By | Created Date | Due date | Start date | Is Recurring | Late | Completed Date | Completed By | Completed Checklist Items | Checklist Items | Labels | Notes
l6PhGHMs-UajYSX99mFtBMkANdNL | Assign team roles | m628UmO0_kmsMJLMNZTH48kAIFPo |  | Completed | Important | d9d174d5-83da-4dc8-b3b3-47d32169d8b3;3da3c651-7618-4988-8b39-cbc5279b1753;f1d24dba-7ca3-4384-b194-da338a5a6922;52ec3f15-0be7-4770-9ec8-2364e806d08b | d9d174d5-83da-4dc8-b3b3-47d32169d8b3 | 2026-08-26 | 2025-10-22 |  |  | false | 2026-08-26 | d9d174d5-83da-4dc8-b3b3-47d32169d8b3
FkS0p3dd5kq8_v_i16cEJckAKDK3 | Conduct initial meeting | m628UmO0_kmsMJLMNZTH48kAIFPo |  | Completed | Medium | d9d174d5-83da-4dc8-b3b3-47d32169d8b3;3da3c651-7618-4988-8b39-cbc5279b1753;f1d24dba-7ca3-4384-b194-da338a5a6922;52ec3f15-0be7-4770-9ec8-2364e806d08b | d9d174d5-83da-4dc8-b3b3-47d32169d8b3 | 2026-08-26 | 2025-10-22 |  |  | false | 2026-10-14 | 52ec3f15-0be7-4770-9ec8-2364e806d08b
q5xU3SQC8EGsTMsaiP2r38kAO_u9 | Submit the research group form | m628UmO0_kmsMJLMNZTH48kAIFPo |  | Completed | Urgent | 52ec3f15-0be7-4770-9ec8-2364e806d08b | d9d174d5-83da-4dc8-b3b3-47d32169d8b3 | 2026-08-26 | 2025-10-25 |  |  | false | 2026-10-14 | 52ec3f15-0be7-4770-9ec8-2364e806d08b
qjbP4CkTEUuUcU1QhxrH2skAKhn8 | Get initial approval | m628UmO0_kmsMJLMNZTH48kAIFPo |  | Completed | Important | d9d174d5-83da-4dc8-b3b3-47d32169d8b3;3da3c651-7618-4988-8b39-cbc5279b1753;f1d24dba-7ca3-4384-b194-da338a5a6922;52ec3f15-0be7-4770-9ec8-2364e806d08b | d9d174d5-83da-4dc8-b3b3-47d32169d8b3 | 2026-08-26 | 2025-11-18 |  |  | false | 2026-10-14 | d9d174d5-83da-4dc8-b3b3-47d32169d8b3
NhCPvUnmO0ORNkNmArFTvMkAElQ_ | Review current EV management problems and user pain points | dZ3sRVli30e4_Shmpfbu6skAPzPW |  | Completed | Important | d9d174d5-83da-4dc8-b3b3-47d32169d8b3;3da3c651-7618-4988-8b39-cbc5279b1753;f1d24dba-7ca3-4384-b194-da338a5a6922;52ec3f15-0be7-4770-9ec8-2364e806d08b | d9d174d5-83da-4dc8-b3b3-47d32169d8b3 | 2026-08-28 |  |  |  | false | 2026-08-28 | d9d174d5-83da-4dc8-b3b3-47d32169d8b3
GGo-22naPEGflUn4TYZoGskAN_ry | Define the main research problem | dZ3sRVli30e4_Shmpfbu6skAPzPW |  | Completed | Urgent | d9d174d5-83da-4dc8-b3b3-47d32169d8b3;3da3c651-7618-4988-8b39-cbc5279b1753;f1d24dba-7ca3-4384-b194-da338a5a6922;52ec3f15-0be7-4770-9ec8-2364e806d08b | d9d174d5-83da-4dc8-b3b3-47d32169d8b3 | 2026-08-28 |  |  |  | false | 2026-08-28 | d9d174d5-83da-4dc8-b3b3-47d32169d8b3
DhVL37Q8aEe17sFtXwE5C8kAChrH | Identify four independent novelty components | dZ3sRVli30e4_Shmpfbu6skAPzPW |  | Completed | Important | d9d174d5-83da-4dc8-b3b3-47d32169d8b3;3da3c651-7618-4988-8b39-cbc5279b1753;f1d24dba-7ca3-4384-b194-da338a5a6922;52ec3f15-0be7-4770-9ec8-2364e806d08b | d9d174d5-83da-4dc8-b3b3-47d32169d8b3 | 2026-08-28 |  |  |  | false | 2026-08-28 | d9d174d5-83da-4dc8-b3b3-47d32169d8b3
kUvROvBMzU21U-MCxDvGJskAIOCx | Component 1 – EV Operational Anomaly Detection | dZ3sRVli30e4_Shmpfbu6skAPzPW |  | Completed | Urgent | 52ec3f15-0be7-4770-9ec8-2364e806d08b | d9d174d5-83da-4dc8-b3b3-47d32169d8b3 | 2026-08-28 |  |  |  | false | 2026-08-30 | 52ec3f15-0be7-4770-9ec8-2364e806d08b
pvfOojKHNEOMQOjAdbnJbskAD4mS | Component 2 – Adaptive Battery Health Prediction | dZ3sRVli30e4_Shmpfbu6skAPzPW |  | Completed | Important | d9d174d5-83da-4dc8-b3b3-47d32169d8b3 | d9d174d5-83da-4dc8-b3b3-47d32169d8b3 | 2026-08-28 |  |  |  | false | 2026-08-28 | d9d174d5-83da-4dc8-b3b3-47d32169d8b3
B4JBxzpOBU-ucKhMBXqxnMkAILmo | Component 3 – Charging Optimization & Range Prediction | dZ3sRVli30e4_Shmpfbu6skAPzPW |  | Completed | Important | f1d24dba-7ca3-4384-b194-da338a5a6922 | d9d174d5-83da-4dc8-b3b3-47d32169d8b3 | 2026-08-28 |  |  |  | false | 2026-08-31 | f1d24dba-7ca3-4384-b194-da338a5a6922
53gKv62QH0WbeknsGKCrLskAACp6 | Prepare initial problem statement and research justification | QKZv960-W0iweSNTennTsskANYXx |  | Completed | Important | d9d174d5-83da-4dc8-b3b3-47d32169d8b3;3da3c651-7618-4988-8b39-cbc5279b1753;f1d24dba-7ca3-4384-b194-da338a5a6922;52ec3f15-0be7-4770-9ec8-2364e806d08b | d9d174d5-83da-4dc8-b3b3-47d32169d8b3 | 2026-08-28 |  |  |  | false | 2026-08-28 | d9d174d5-83da-4dc8-b3b3-47d32169d8b3
bF6OlCkxbEmynNxZgGfekckAMoHB | Prepare novelty and research-gap summary | QKZv960-W0iweSNTennTsskANYXx |  | Completed | Important | d9d174d5-83da-4dc8-b3b3-47d32169d8b3;3da3c651-7618-4988-8b39-cbc5279b1753;f1d24dba-7ca3-4384-b194-da338a5a6922;52ec3f15-0be7-4770-9ec8-2364e806d08b | d9d174d5-83da-4dc8-b3b3-47d32169d8b3 | 2026-08-28 |  |  |  | false | 2026-08-28 | d9d174d5-83da-4dc8-b3b3-47d32169d8b3
Z-SrjetcP0KQ6La0nQsEKckAMplh | Prepare TAF / topic approval document | QKZv960-W0iweSNTennTsskANYXx |  | Completed | Urgent | d9d174d5-83da-4dc8-b3b3-47d32169d8b3;3da3c651-7618-4988-8b39-cbc5279b1753;f1d24dba-7ca3-4384-b194-da338a5a6922;52ec3f15-0be7-4770-9ec8-2364e806d08b | d9d174d5-83da-4dc8-b3b3-47d32169d8b3 | 2026-08-28 |  |  |  | false | 2026-08-28 | d9d174d5-83da-4dc8-b3b3-47d32169d8b3
dUw29kygJEmeihlSjZSjvMkAKr7R | Submit TAF and attend evaluation | QKZv960-W0iweSNTennTsskANYXx |  | Completed | Urgent | d9d174d5-83da-4dc8-b3b3-47d32169d8b3;3da3c651-7618-4988-8b39-cbc5279b1753;f1d24dba-7ca3-4384-b194-da338a5a6922;52ec3f15-0be7-4770-9ec8-2364e806d08b | d9d174d5-83da-4dc8-b3b3-47d32169d8b3 | 2026-08-28 |  |  |  | false | 2026-08-28 | d9d174d5-83da-4dc8-b3b3-47d32169d8b3
IAVc8NaQ_EGw-Z_3bF34KMkAK84z | Draft charter | Efnm-wRdGUmSH4CmaLN72MkAMIP4 |  | Completed | Medium | d9d174d5-83da-4dc8-b3b3-47d32169d8b3;3da3c651-7618-4988-8b39-cbc5279b1753;f1d24dba-7ca3-4384-b194-da338a5a6922;52ec3f15-0be7-4770-9ec8-2364e806d08b | d9d174d5-83da-4dc8-b3b3-47d32169d8b3 | 2026-08-28 |  |  |  | false | 2026-08-28 | d9d174d5-83da-4dc8-b3b3-47d32169d8b3
meL2Qp1T8kGedA76m0mEwskAPqbE | Prepare timeline | Efnm-wRdGUmSH4CmaLN72MkAMIP4 |  | Completed | Medium | d9d174d5-83da-4dc8-b3b3-47d32169d8b3;3da3c651-7618-4988-8b39-cbc5279b1753;f1d24dba-7ca3-4384-b194-da338a5a6922;52ec3f15-0be7-4770-9ec8-2364e806d08b | d9d174d5-83da-4dc8-b3b3-47d32169d8b3 | 2026-08-28 |  |  |  | false | 2026-08-28 | d9d174d5-83da-4dc8-b3b3-47d32169d8b3
vbO3MCqHdUGeehL_f_-mgMkALcQy | Submit charter | Efnm-wRdGUmSH4CmaLN72MkAMIP4 |  | Completed | Medium | 52ec3f15-0be7-4770-9ec8-2364e806d08b | d9d174d5-83da-4dc8-b3b3-47d32169d8b3 | 2026-08-28 |  |  |  | false | 2026-08-30 | 52ec3f15-0be7-4770-9ec8-2364e806d08b
6qe8JmjeOU-XJZJnODWwTckAH7tg | Prepare Proposal – EV Operational Anomaly Detection | nbYfgup8oUiwbO4khE_03ckAGWMj |  | Completed | Medium | 52ec3f15-0be7-4770-9ec8-2364e806d08b | d9d174d5-83da-4dc8-b3b3-47d32169d8b3 | 2026-08-28 |  |  |  | false | 2026-08-30 | 52ec3f15-0be7-4770-9ec8-2364e806d08b
Qu23s96xN0eMwZIZENcY9ckAK7Cn | Prepare Proposal – Adaptive Battery Health Prediction and Personalized Recommendation | nbYfgup8oUiwbO4khE_03ckAGWMj |  | Completed | Medium | d9d174d5-83da-4dc8-b3b3-47d32169d8b3 | d9d174d5-83da-4dc8-b3b3-47d32169d8b3 | 2026-08-28 |  |  |  | false | 2026-08-28 | d9d174d5-83da-4dc8-b3b3-47d32169d8b3
RsW4E0RjeEKYrlsmvmz9LskAJyIe | Prepare Proposal – Charging Optimization & Range Prediction | nbYfgup8oUiwbO4khE_03ckAGWMj |  | Completed | Medium | f1d24dba-7ca3-4384-b194-da338a5a6922 | d9d174d5-83da-4dc8-b3b3-47d32169d8b3 | 2026-08-28 |  |  |  | false | 2026-08-31 | f1d24dba-7ca3-4384-b194-da338a5a6922
ie1_3JqkTESJIc7yJurOKskAIv_0 | Prepare Proposal –AI-Based EV Virtual Assistant | nbYfgup8oUiwbO4khE_03ckAGWMj |  | Completed | Medium | 3da3c651-7618-4988-8b39-cbc5279b1753 | d9d174d5-83da-4dc8-b3b3-47d32169d8b3 | 2026-08-28 |  |  |  | false | 2026-08-30 | 52ec3f15-0be7-4770-9ec8-2364e806d08b
Vf7ge5kitEyohldjce9DmMkAI4Tv | Upload Individual Proposal Documents to CDAP Cloud Storage | nbYfgup8oUiwbO4khE_03ckAGWMj |  | Completed | Urgent | d9d174d5-83da-4dc8-b3b3-47d32169d8b3;3da3c651-7618-4988-8b39-cbc5279b1753;f1d24dba-7ca3-4384-b194-da338a5a6922;52ec3f15-0be7-4770-9ec8-2364e806d08b | d9d174d5-83da-4dc8-b3b3-47d32169d8b3 | 2026-08-28 | 2026-03-16 |  |  | false | 2026-08-28 | d9d174d5-83da-4dc8-b3b3-47d32169d8b3
JmjqSqSoyEyxvN4ab00OHMkAO0qK | Prepare Presentation Slides | L3EJ3uU6C02_HrVfyiX3KMkAOYC2 |  | Completed | Important | d9d174d5-83da-4dc8-b3b3-47d32169d8b3;3da3c651-7618-4988-8b39-cbc5279b1753;f1d24dba-7ca3-4384-b194-da338a5a6922;52ec3f15-0be7-4770-9ec8-2364e806d08b | d9d174d5-83da-4dc8-b3b3-47d32169d8b3 | 2026-08-28 |  |  |  | false | 2026-08-28 | d9d174d5-83da-4dc8-b3b3-47d32169d8b3
bKQ_pi7J9UufCJ1ib4taHckAPC61 | Finalize Proposal Presentation Slides | L3EJ3uU6C02_HrVfyiX3KMkAOYC2 |  | Completed | Important | d9d174d5-83da-4dc8-b3b3-47d32169d8b3;3da3c651-7618-4988-8b39-cbc5279b1753;f1d24dba-7ca3-4384-b194-da338a5a6922;52ec3f15-0be7-4770-9ec8-2364e806d08b | d9d174d5-83da-4dc8-b3b3-47d32169d8b3 | 2026-08-28 |  |  |  | false | 2026-08-28 | d9d174d5-83da-4dc8-b3b3-47d32169d8b3
QcPABT1Y5kyZ5YqYAAV0iMkAPvi9 | Meet with Supervisor Before Proposal Presentation | L3EJ3uU6C02_HrVfyiX3KMkAOYC2 |  | Completed | Medium | d9d174d5-83da-4dc8-b3b3-47d32169d8b3;3da3c651-7618-4988-8b39-cbc5279b1753;f1d24dba-7ca3-4384-b194-da338a5a6922;52ec3f15-0be7-4770-9ec8-2364e806d08b | d9d174d5-83da-4dc8-b3b3-47d32169d8b3 | 2026-08-28 |  |  |  | false | 2026-08-28 | d9d174d5-83da-4dc8-b3b3-47d32169d8b3
MydYu4aCy0OY-1sHI2c6QskAN0Fq | Conduct Proposal Presentation to Panel | L3EJ3uU6C02_HrVfyiX3KMkAOYC2 |  | Completed | Important | d9d174d5-83da-4dc8-b3b3-47d32169d8b3;3da3c651-7618-4988-8b39-cbc5279b1753;f1d24dba-7ca3-4384-b194-da338a5a6922;52ec3f15-0be7-4770-9ec8-2364e806d08b | d9d174d5-83da-4dc8-b3b3-47d32169d8b3 | 2026-08-28 | 2026-03-16 |  |  | false | 2026-08-28 | d9d174d5-83da-4dc8-b3b3-47d32169d8b3
DdiZ1bU8Uk-3C-5jXMEHN8kAJgfU | Finalize research topic title - Electric Vehicle Management System Using Artificial Intelligence and Machine Learning | PxFW6OzeK0WuClqZfCsLE8kAGmH7 |  | Completed | Important | d9d174d5-83da-4dc8-b3b3-47d32169d8b3;3da3c651-7618-4988-8b39-cbc5279b1753;f1d24dba-7ca3-4384-b194-da338a5a6922;52ec3f15-0be7-4770-9ec8-2364e806d08b | d9d174d5-83da-4dc8-b3b3-47d32169d8b3 | 2026-08-28 |  |  |  | false | 2026-08-28 | d9d174d5-83da-4dc8-b3b3-47d32169d8b3
fPKUCnrCwEy7Lb2FPzijdMkAAWhX | Found supervisor and co supervisor | PxFW6OzeK0WuClqZfCsLE8kAGmH7 |  | Completed | Urgent | d9d174d5-83da-4dc8-b3b3-47d32169d8b3;3da3c651-7618-4988-8b39-cbc5279b1753;f1d24dba-7ca3-4384-b194-da338a5a6922;52ec3f15-0be7-4770-9ec8-2364e806d08b | d9d174d5-83da-4dc8-b3b3-47d32169d8b3 | 2026-08-28 |  |  |  | false | 2026-08-28 | d9d174d5-83da-4dc8-b3b3-47d32169d8b3
X755i-7ZDkinbUm7g5f48skAGOLa | Component 4 - Finalize Predictive Charging & Breakdown Assistance System | dZ3sRVli30e4_Shmpfbu6skAPzPW |  | Completed | Important | 3da3c651-7618-4988-8b39-cbc5279b1753 | 3da3c651-7618-4988-8b39-cbc5279b1753 | 2026-08-30 |  |  |  | false | 2026-08-30 | 3da3c651-7618-4988-8b39-cbc5279b1753 | 7/7 | Define objectives for each component;Analyze feasibility of selected ideas;Finalize the complete project title;Identify 4 novelty component ideas;Select main project domain (AI & ML);Evaluate uniqueness & innovation level of components;Brainstorm research ideas
WXTvBOVYVUyV6uN4PL2pN8kAL5FD | Discuss topic ideas with supervisor | m628UmO0_kmsMJLMNZTH48kAIFPo |  | Completed | Important | d9d174d5-83da-4dc8-b3b3-47d32169d8b3;3da3c651-7618-4988-8b39-cbc5279b1753;f1d24dba-7ca3-4384-b194-da338a5a6922;52ec3f15-0be7-4770-9ec8-2364e806d08b | 3da3c651-7618-4988-8b39-cbc5279b1753 | 2026-08-30 |  |  |  | false | 2026-10-14 | d9d174d5-83da-4dc8-b3b3-47d32169d8b3 | 2/2 | Get initial approval;Discuss topic with supervisor
uyc087d95Em6LqUqOf7NeskAObO5 | Review related research papers and Identify contradictions or gaps | QKZv960-W0iweSNTennTsskANYXx |  | Completed | Important | 3da3c651-7618-4988-8b39-cbc5279b1753 | 3da3c651-7618-4988-8b39-cbc5279b1753 | 2026-08-30 |  |  |  | false | 2026-08-30 | 3da3c651-7618-4988-8b39-cbc5279b1753 | 7/7 | Revise scope;Attend evaluation;Record supervisor comments;Complete TAF form and Review using TAF guideline;Confirm data availability and Identify key stakeholders;Defined research problem;Submit TAF for supervisor approval
uuS0K5KkEUaz3lXY1b-_vskAJBB7 | Create GitHub Repository | ACEgOwj4Ukafa8Q-iv7ApMkAMJwI |  | Completed | Important | 52ec3f15-0be7-4770-9ec8-2364e806d08b | d9d174d5-83da-4dc8-b3b3-47d32169d8b3 | 2026-10-14 | 2026-03-10 |  |  | false | 2026-10-14 | 52ec3f15-0be7-4770-9ec8-2364e806d08b
Qrz89X7DVkuEb8ZZ71zT0ckAOdgX | Define Repository Structure & Folder Organization | ACEgOwj4Ukafa8Q-iv7ApMkAMJwI |  | Completed | Medium | 52ec3f15-0be7-4770-9ec8-2364e806d08b | d9d174d5-83da-4dc8-b3b3-47d32169d8b3 | 2026-10-14 | 2026-05-13 |  |  | false | 2026-10-14 | 52ec3f15-0be7-4770-9ec8-2364e806d08b
dGjzrpftg0GXpX_4DflWI8kAJTG9 | Create Feature Branches for Individual Components | ACEgOwj4Ukafa8Q-iv7ApMkAMJwI |  | Completed | Medium | d9d174d5-83da-4dc8-b3b3-47d32169d8b3;3da3c651-7618-4988-8b39-cbc5279b1753;f1d24dba-7ca3-4384-b194-da338a5a6922;52ec3f15-0be7-4770-9ec8-2364e806d08b | d9d174d5-83da-4dc8-b3b3-47d32169d8b3 | 2026-10-14 |  |  |  | false | 2026-10-14 | d9d174d5-83da-4dc8-b3b3-47d32169d8b3
4LqW2QJxx0W2o23dksLdrMkAGhUL | Update README File with Project Overview & Architecture | ACEgOwj4Ukafa8Q-iv7ApMkAMJwI |  | Completed | Medium | d9d174d5-83da-4dc8-b3b3-47d32169d8b3;3da3c651-7618-4988-8b39-cbc5279b1753;f1d24dba-7ca3-4384-b194-da338a5a6922;52ec3f15-0be7-4770-9ec8-2364e806d08b | d9d174d5-83da-4dc8-b3b3-47d32169d8b3 | 2026-10-14 |  |  |  | false | 2026-10-14 | d9d174d5-83da-4dc8-b3b3-47d32169d8b3
a61Cq1VmBUSHf-Nyspur7skAG4qt | Develop Individual Component for PP 1 (AI-Based EV Operational Anomaly Detection) | maWPzgr43ECIZM0OKcmkTskAD5LP |  | Completed | Medium | 52ec3f15-0be7-4770-9ec8-2364e806d08b | d9d174d5-83da-4dc8-b3b3-47d32169d8b3 | 2026-10-14 | 2026-05-11 |  |  | false | 2026-10-14 | 52ec3f15-0be7-4770-9ec8-2364e806d08b
LEzonIOlqEWu1Dls3uCfV8kADF0z | Develop Individual Component for PP 1 (Adaptive Battery Health Prediction and Personalized Recommendation) | maWPzgr43ECIZM0OKcmkTskAD5LP |  | Completed | Medium | d9d174d5-83da-4dc8-b3b3-47d32169d8b3 | d9d174d5-83da-4dc8-b3b3-47d32169d8b3 | 2026-10-14 |  |  |  | false | 2026-10-14 | d9d174d5-83da-4dc8-b3b3-47d32169d8b3
DoXNsegPSkS56j9fsmXPK8kAFz5T | Develop Individual Component for PP 1 (Intelligent EV Charging Optimization and Range Prediction) | maWPzgr43ECIZM0OKcmkTskAD5LP |  | Completed | Medium | f1d24dba-7ca3-4384-b194-da338a5a6922 | d9d174d5-83da-4dc8-b3b3-47d32169d8b3 | 2026-10-14 |  |  |  | false | 2026-10-14 | f1d24dba-7ca3-4384-b194-da338a5a6922
itsHdCjSAUK3vwimNeRd8skACJS7 | Develop Individual Component for PP 1 (AI-Based EV Virtual Assistant) | maWPzgr43ECIZM0OKcmkTskAD5LP |  | Completed | Medium | 3da3c651-7618-4988-8b39-cbc5279b1753 | d9d174d5-83da-4dc8-b3b3-47d32169d8b3 | 2026-10-14 |  |  |  | false | 2026-10-14 | d9d174d5-83da-4dc8-b3b3-47d32169d8b3
nLD4fCg1302n2k0aXOZKFMkAKiqN | Prepare individual module slides | VlO41rPqGEOQ2Lw1BrY6T8kAJT8T |  | Completed | Medium | d9d174d5-83da-4dc8-b3b3-47d32169d8b3;3da3c651-7618-4988-8b39-cbc5279b1753;f1d24dba-7ca3-4384-b194-da338a5a6922;52ec3f15-0be7-4770-9ec8-2364e806d08b | d9d174d5-83da-4dc8-b3b3-47d32169d8b3 | 2026-10-14 |  |  |  | false | 2026-10-14 | d9d174d5-83da-4dc8-b3b3-47d32169d8b3
vfnIt8-YEES4DXoiK9SLgMkAJFo7 | Finalize Progress Presentation-1 Slides | VlO41rPqGEOQ2Lw1BrY6T8kAJT8T |  | Completed | Medium | d9d174d5-83da-4dc8-b3b3-47d32169d8b3 | d9d174d5-83da-4dc8-b3b3-47d32169d8b3 | 2026-10-14 |  |  |  | false | 2026-10-14 | d9d174d5-83da-4dc8-b3b3-47d32169d8b3
iyEPWiQ_4kmNMMI5fkGsickAKzhk | Meet with Supervisor Before Progress Presentation-1 | VlO41rPqGEOQ2Lw1BrY6T8kAJT8T |  | Completed | Medium | d9d174d5-83da-4dc8-b3b3-47d32169d8b3;3da3c651-7618-4988-8b39-cbc5279b1753;f1d24dba-7ca3-4384-b194-da338a5a6922;52ec3f15-0be7-4770-9ec8-2364e806d08b | d9d174d5-83da-4dc8-b3b3-47d32169d8b3 | 2026-10-14 |  |  |  | false | 2026-10-14 | d9d174d5-83da-4dc8-b3b3-47d32169d8b3
SjawLahGFkOrU7GyqVTjeckAKiGp | Prepare Speaking Notes | VlO41rPqGEOQ2Lw1BrY6T8kAJT8T |  | Completed | Medium | d9d174d5-83da-4dc8-b3b3-47d32169d8b3;3da3c651-7618-4988-8b39-cbc5279b1753;f1d24dba-7ca3-4384-b194-da338a5a6922;52ec3f15-0be7-4770-9ec8-2364e806d08b | d9d174d5-83da-4dc8-b3b3-47d32169d8b3 | 2026-10-14 |  |  |  | false | 2026-10-14 | d9d174d5-83da-4dc8-b3b3-47d32169d8b3
g9M9qOkl7kukkdKEFggZH8kAKUjS | Conduct Progress Presentation-1 to Panel | VlO41rPqGEOQ2Lw1BrY6T8kAJT8T |  | Completed | Important | d9d174d5-83da-4dc8-b3b3-47d32169d8b3;3da3c651-7618-4988-8b39-cbc5279b1753;f1d24dba-7ca3-4384-b194-da338a5a6922 | d9d174d5-83da-4dc8-b3b3-47d32169d8b3 | 2026-10-14 | 2026-05-11 |  |  | false | 2026-10-14 | d9d174d5-83da-4dc8-b3b3-47d32169d8b3
ZEakAIhS80mVrJR0b5s_IMkADWzR | Submit Progress Presentation 1 (PP1) | VlO41rPqGEOQ2Lw1BrY6T8kAJT8T |  | Completed | Medium | 52ec3f15-0be7-4770-9ec8-2364e806d08b | d9d174d5-83da-4dc8-b3b3-47d32169d8b3 | 2026-10-14 | 2026-05-11 |  |  | false | 2026-10-14 | 52ec3f15-0be7-4770-9ec8-2364e806d08b
AzDP16qFdEq5fOxs0wS_1MkAEQm_ | Review Immediate Verbal Feedback from PP1 | ZdUdBS3BA0-bW58yGGW_E8kAP2aJ |  | Completed | Medium | d9d174d5-83da-4dc8-b3b3-47d32169d8b3;3da3c651-7618-4988-8b39-cbc5279b1753;f1d24dba-7ca3-4384-b194-da338a5a6922;52ec3f15-0be7-4770-9ec8-2364e806d08b | d9d174d5-83da-4dc8-b3b3-47d32169d8b3 | 2026-10-14 |  |  |  | false | 2026-10-14 | d9d174d5-83da-4dc8-b3b3-47d32169d8b3
dWW7kGW46EW1IeWkRaeBy8kAKUE6 | Discuss Official Panel Comments with Supervisor | ZdUdBS3BA0-bW58yGGW_E8kAP2aJ |  | Completed | Medium | d9d174d5-83da-4dc8-b3b3-47d32169d8b3;3da3c651-7618-4988-8b39-cbc5279b1753;f1d24dba-7ca3-4384-b194-da338a5a6922;52ec3f15-0be7-4770-9ec8-2364e806d08b | d9d174d5-83da-4dc8-b3b3-47d32169d8b3 | 2026-10-14 |  |  |  | false | 2026-10-14 | d9d174d5-83da-4dc8-b3b3-47d32169d8b3
_si6_ku4Y0qWBvV_pAwn38kANW7d | Implement Initial Improvements Based on Verbal Feedback | ZdUdBS3BA0-bW58yGGW_E8kAP2aJ |  | Completed | Medium | d9d174d5-83da-4dc8-b3b3-47d32169d8b3;3da3c651-7618-4988-8b39-cbc5279b1753;f1d24dba-7ca3-4384-b194-da338a5a6922;52ec3f15-0be7-4770-9ec8-2364e806d08b | d9d174d5-83da-4dc8-b3b3-47d32169d8b3 | 2026-10-14 |  |  |  | false | 2026-10-14 | d9d174d5-83da-4dc8-b3b3-47d32169d8b3
LcsutcMT4Em85i-sRSkfH8kAE6Ri | Receive & Review Official Panel Comments (Written) | ZdUdBS3BA0-bW58yGGW_E8kAP2aJ |  | Completed | Medium | d9d174d5-83da-4dc8-b3b3-47d32169d8b3;3da3c651-7618-4988-8b39-cbc5279b1753;f1d24dba-7ca3-4384-b194-da338a5a6922;52ec3f15-0be7-4770-9ec8-2364e806d08b | d9d174d5-83da-4dc8-b3b3-47d32169d8b3 | 2026-10-14 |  |  |  | false | 2026-10-14 | d9d174d5-83da-4dc8-b3b3-47d32169d8b3
h4e-K5MruUORaTQdyXisnskABVO3 | Implement Improvements Based on Official panel Comments | ZdUdBS3BA0-bW58yGGW_E8kAP2aJ |  | Completed | Medium | d9d174d5-83da-4dc8-b3b3-47d32169d8b3;3da3c651-7618-4988-8b39-cbc5279b1753;f1d24dba-7ca3-4384-b194-da338a5a6922;52ec3f15-0be7-4770-9ec8-2364e806d08b | d9d174d5-83da-4dc8-b3b3-47d32169d8b3 | 2026-10-14 |  |  |  | false | 2026-10-14 | d9d174d5-83da-4dc8-b3b3-47d32169d8b3
V8DmFE4dc0ep-Yix1AAOaskAJ9dP | System Integration – Combine All Modules | ZdUdBS3BA0-bW58yGGW_E8kAP2aJ |  | Completed | Medium | d9d174d5-83da-4dc8-b3b3-47d32169d8b3;3da3c651-7618-4988-8b39-cbc5279b1753;f1d24dba-7ca3-4384-b194-da338a5a6922;52ec3f15-0be7-4770-9ec8-2364e806d08b | d9d174d5-83da-4dc8-b3b3-47d32169d8b3 | 2026-10-14 |  |  |  | false | 2026-10-14 | d9d174d5-83da-4dc8-b3b3-47d32169d8b3
7GLeNHnr9UWr6uvAhKqt0MkAIzML | Prepare Checklist 2 – MS Planner Management Review | ZdUdBS3BA0-bW58yGGW_E8kAP2aJ |  | Completed | Medium | d9d174d5-83da-4dc8-b3b3-47d32169d8b3 | d9d174d5-83da-4dc8-b3b3-47d32169d8b3 | 2026-10-14 |  |  |  | false | 2026-10-14 | d9d174d5-83da-4dc8-b3b3-47d32169d8b3
xtPCw0_IRkaQbFo5aa3KcckAJi0c | Finalize Progress Presentation- 2 Slides | ZdUdBS3BA0-bW58yGGW_E8kAP2aJ |  | Completed | Medium | d9d174d5-83da-4dc8-b3b3-47d32169d8b3;3da3c651-7618-4988-8b39-cbc5279b1753;f1d24dba-7ca3-4384-b194-da338a5a6922;52ec3f15-0be7-4770-9ec8-2364e806d08b | d9d174d5-83da-4dc8-b3b3-47d32169d8b3 | 2026-10-14 |  |  |  | false | 2026-10-14 | d9d174d5-83da-4dc8-b3b3-47d32169d8b3
MfcYyM30Z06a7qMYo35zVMkAItei | Meet with Supervisor Before Progress Presentation-2 | ZdUdBS3BA0-bW58yGGW_E8kAP2aJ |  | Completed | Medium | d9d174d5-83da-4dc8-b3b3-47d32169d8b3;3da3c651-7618-4988-8b39-cbc5279b1753;f1d24dba-7ca3-4384-b194-da338a5a6922;52ec3f15-0be7-4770-9ec8-2364e806d08b | d9d174d5-83da-4dc8-b3b3-47d32169d8b3 | 2026-10-14 |  |  |  | false | 2026-10-14 | d9d174d5-83da-4dc8-b3b3-47d32169d8b3
T4XoDKZGn0KP4n_2S42nuskAOnAC | Prepare Speaking Notes | ZdUdBS3BA0-bW58yGGW_E8kAP2aJ |  | Completed | Medium | d9d174d5-83da-4dc8-b3b3-47d32169d8b3;3da3c651-7618-4988-8b39-cbc5279b1753;f1d24dba-7ca3-4384-b194-da338a5a6922;52ec3f15-0be7-4770-9ec8-2364e806d08b | d9d174d5-83da-4dc8-b3b3-47d32169d8b3 | 2026-10-14 |  |  |  | false | 2026-10-14 | d9d174d5-83da-4dc8-b3b3-47d32169d8b3
lq4EnTedGki5Gntm_hK3h8kAPGoJ | Conduct Progress Presentation-2 to Panel | ZdUdBS3BA0-bW58yGGW_E8kAP2aJ |  | Completed | Medium | d9d174d5-83da-4dc8-b3b3-47d32169d8b3;3da3c651-7618-4988-8b39-cbc5279b1753;f1d24dba-7ca3-4384-b194-da338a5a6922;52ec3f15-0be7-4770-9ec8-2364e806d08b | d9d174d5-83da-4dc8-b3b3-47d32169d8b3 | 2026-10-14 | 2026-08-31 |  |  | false | 2026-10-14 | d9d174d5-83da-4dc8-b3b3-47d32169d8b3
-WYrHYoVBEKHsloqiYl5VckAOfSw | Submit Progress Presentation 2 (PP2) | ZdUdBS3BA0-bW58yGGW_E8kAP2aJ |  | Completed | Medium | 52ec3f15-0be7-4770-9ec8-2364e806d08b | d9d174d5-83da-4dc8-b3b3-47d32169d8b3 | 2026-10-14 | 2026-08-31 | 2026-08-31 |  | false | 2026-10-14 | 52ec3f15-0be7-4770-9ec8-2364e806d08b
6hXYPp0nk0q_qFWO4yq448kANVgt | Individual draft thesis ready | 9yeUdI2tT0GsQn-2iPIr0MkAOa1I |  | Completed | Medium | d9d174d5-83da-4dc8-b3b3-47d32169d8b3;3da3c651-7618-4988-8b39-cbc5279b1753;f1d24dba-7ca3-4384-b194-da338a5a6922;52ec3f15-0be7-4770-9ec8-2364e806d08b | d9d174d5-83da-4dc8-b3b3-47d32169d8b3 | 2026-10-14 |  |  |  | false | 2026-10-14 | d9d174d5-83da-4dc8-b3b3-47d32169d8b3
LvmdEYb0zE-vG_lIkameJ8kALdax | Group draft thesis ready | 9yeUdI2tT0GsQn-2iPIr0MkAOa1I |  | Completed | Medium | d9d174d5-83da-4dc8-b3b3-47d32169d8b3;3da3c651-7618-4988-8b39-cbc5279b1753;f1d24dba-7ca3-4384-b194-da338a5a6922 | d9d174d5-83da-4dc8-b3b3-47d32169d8b3 | 2026-10-14 |  |  |  | false | 2026-10-14 | d9d174d5-83da-4dc8-b3b3-47d32169d8b3
pbORX9eSSUK_I4vYamiY98kAK1Uu | Individual draft thesis submit | 9yeUdI2tT0GsQn-2iPIr0MkAOa1I |  | Completed | Important | d9d174d5-83da-4dc8-b3b3-47d32169d8b3;3da3c651-7618-4988-8b39-cbc5279b1753;f1d24dba-7ca3-4384-b194-da338a5a6922;52ec3f15-0be7-4770-9ec8-2364e806d08b | d9d174d5-83da-4dc8-b3b3-47d32169d8b3 | 2026-10-14 | 2026-10-11 |  |  | false | 2026-10-14 | d9d174d5-83da-4dc8-b3b3-47d32169d8b3
Xu3clPnLxUmkXYzxYP5m98kAA7Ma | Group draft thesis submit | 9yeUdI2tT0GsQn-2iPIr0MkAOa1I |  | Completed | Important | 52ec3f15-0be7-4770-9ec8-2364e806d08b | d9d174d5-83da-4dc8-b3b3-47d32169d8b3 | 2026-10-14 | 2026-10-11 |  |  | false | 2026-10-14 | 52ec3f15-0be7-4770-9ec8-2364e806d08b
RKVFew04_Eq8KoHOGh_KqMkAGJcJ | Create and initialize repository | PDFlT4uHbUGrvuN36kHcjckAMWBJ |  | Completed | Medium | d9d174d5-83da-4dc8-b3b3-47d32169d8b3 | d9d174d5-83da-4dc8-b3b3-47d32169d8b3 | 2026-10-14 |  |  |  | false | 2026-10-14 | d9d174d5-83da-4dc8-b3b3-47d32169d8b3
VUB4vD3FfUGytZueX3YM9MkAHGzS | Requirements analysis for create website | PDFlT4uHbUGrvuN36kHcjckAMWBJ |  | Completed | Medium | d9d174d5-83da-4dc8-b3b3-47d32169d8b3 | d9d174d5-83da-4dc8-b3b3-47d32169d8b3 | 2026-10-14 |  |  |  | false | 2026-10-14 | d9d174d5-83da-4dc8-b3b3-47d32169d8b3
LUTOMLEfNkiPwiQz4NdVbckALglR | Deploy website | PDFlT4uHbUGrvuN36kHcjckAMWBJ |  | Completed | Medium | d9d174d5-83da-4dc8-b3b3-47d32169d8b3 | d9d174d5-83da-4dc8-b3b3-47d32169d8b3 | 2026-10-14 |  |  |  | false | 2026-10-14 | d9d174d5-83da-4dc8-b3b3-47d32169d8b3
D2QbxjMCqEGkZeaBr8nEEskAKmZQ | UI modifications complete | PDFlT4uHbUGrvuN36kHcjckAMWBJ |  | Completed | Medium | d9d174d5-83da-4dc8-b3b3-47d32169d8b3 | d9d174d5-83da-4dc8-b3b3-47d32169d8b3 | 2026-10-14 |  |  |  | false | 2026-10-14 | d9d174d5-83da-4dc8-b3b3-47d32169d8b3
vVhm2Aj3fUmS585yXeTZrskAN_E1 | Prepare and submit link | PDFlT4uHbUGrvuN36kHcjckAMWBJ |  | Completed | Important | 52ec3f15-0be7-4770-9ec8-2364e806d08b | d9d174d5-83da-4dc8-b3b3-47d32169d8b3 | 2026-10-14 | 2026-10-11 |  |  | false | 2026-10-14 | 52ec3f15-0be7-4770-9ec8-2364e806d08b
RBF5ztKfw024ixmpzXOOpskAFm4o | Start to create MS Planner | Dy0c50eeGk6iJt38x4lXoMkAJVRd |  | Completed | Medium | d9d174d5-83da-4dc8-b3b3-47d32169d8b3 | d9d174d5-83da-4dc8-b3b3-47d32169d8b3 | 2026-10-14 |  |  |  | false | 2026-10-14 | d9d174d5-83da-4dc8-b3b3-47d32169d8b3
JgLqytPG7U6T9uZEmG5mM8kAAdlq | Update task status (Completed / In Progress) | Dy0c50eeGk6iJt38x4lXoMkAJVRd |  | Completed | Medium | d9d174d5-83da-4dc8-b3b3-47d32169d8b3;3da3c651-7618-4988-8b39-cbc5279b1753;f1d24dba-7ca3-4384-b194-da338a5a6922;52ec3f15-0be7-4770-9ec8-2364e806d08b | d9d174d5-83da-4dc8-b3b3-47d32169d8b3 | 2026-10-14 |  |  |  | false | 2026-10-14 | d9d174d5-83da-4dc8-b3b3-47d32169d8b3
UbZ1ktDMRkCt9sg_X2ceXckAOzqo | Check due dates are set | Dy0c50eeGk6iJt38x4lXoMkAJVRd |  | Completed | Medium | d9d174d5-83da-4dc8-b3b3-47d32169d8b3 | d9d174d5-83da-4dc8-b3b3-47d32169d8b3 | 2026-10-14 |  |  |  | false | 2026-10-14 | d9d174d5-83da-4dc8-b3b3-47d32169d8b3
W5oHL6afAUW9YdODjGsCc8kAKH2_ | Review all Planner tasks | Dy0c50eeGk6iJt38x4lXoMkAJVRd |  | Completed | Medium | d9d174d5-83da-4dc8-b3b3-47d32169d8b3 | d9d174d5-83da-4dc8-b3b3-47d32169d8b3 | 2026-10-14 |  |  |  | false | 2026-10-14 | d9d174d5-83da-4dc8-b3b3-47d32169d8b3
UOFxpcBi1kuTcbHsuHLPlckAAENS | Submit the checklist | Dy0c50eeGk6iJt38x4lXoMkAJVRd |  | Completed | Important | 52ec3f15-0be7-4770-9ec8-2364e806d08b | d9d174d5-83da-4dc8-b3b3-47d32169d8b3 | 2026-10-14 | 2026-10-14 |  |  | false | 2026-10-14 | 52ec3f15-0be7-4770-9ec8-2364e806d08b
A-IqtnChEU-_7tiUMBluW8kANb0f | Finalize research app | b-NzyhLKo0SN0a2KsujNc8kAJnyr |  | Not started | Medium | d9d174d5-83da-4dc8-b3b3-47d32169d8b3;3da3c651-7618-4988-8b39-cbc5279b1753;f1d24dba-7ca3-4384-b194-da338a5a6922;52ec3f15-0be7-4770-9ec8-2364e806d08b | d9d174d5-83da-4dc8-b3b3-47d32169d8b3 | 2026-10-14 | 2026-10-18 |  |  | false
LwnswY1Y20qputvjoEP74MkANvI8 | Prepare presentation slides | b-NzyhLKo0SN0a2KsujNc8kAJnyr |  | Not started | Medium | d9d174d5-83da-4dc8-b3b3-47d32169d8b3;3da3c651-7618-4988-8b39-cbc5279b1753;f1d24dba-7ca3-4384-b194-da338a5a6922;52ec3f15-0be7-4770-9ec8-2364e806d08b | d9d174d5-83da-4dc8-b3b3-47d32169d8b3 | 2026-10-14 |  |  |  | false
Zxd2eM5oX0a1F75qPMi8K8kANoIE | Practice presentation | b-NzyhLKo0SN0a2KsujNc8kAJnyr |  | Not started | Medium | f1d24dba-7ca3-4384-b194-da338a5a6922;d9d174d5-83da-4dc8-b3b3-47d32169d8b3;3da3c651-7618-4988-8b39-cbc5279b1753;52ec3f15-0be7-4770-9ec8-2364e806d08b | d9d174d5-83da-4dc8-b3b3-47d32169d8b3 | 2026-10-14 |  |  |  | false
PExXJ9Vwkku1sjlh2hmQTskAPW0K | Prepare for questions (Q&A) | b-NzyhLKo0SN0a2KsujNc8kAJnyr |  | Not started | Medium | d9d174d5-83da-4dc8-b3b3-47d32169d8b3;3da3c651-7618-4988-8b39-cbc5279b1753;f1d24dba-7ca3-4384-b194-da338a5a6922;52ec3f15-0be7-4770-9ec8-2364e806d08b | d9d174d5-83da-4dc8-b3b3-47d32169d8b3 | 2026-10-14 |  |  |  | false
Q3l1YE2BrUedxYfo_LWAXckAE8gV | Deliver presentation and attend viva | b-NzyhLKo0SN0a2KsujNc8kAJnyr |  | Not started | Important | d9d174d5-83da-4dc8-b3b3-47d32169d8b3;3da3c651-7618-4988-8b39-cbc5279b1753;f1d24dba-7ca3-4384-b194-da338a5a6922;52ec3f15-0be7-4770-9ec8-2364e806d08b | d9d174d5-83da-4dc8-b3b3-47d32169d8b3 | 2026-10-14 | 2026-10-19 |  |  | false
IcIbwH2q7kqHAT6nv7KbEMkAA2_a | Identify Research Gaps & Define Theoretical FoundationIdentify Research Gaps & Define Theoretical Foundation | BQg0Or7SO0yXdcaNQTWYVMkAK1EX |  | Not started | Medium | f1d24dba-7ca3-4384-b194-da338a5a6922;d9d174d5-83da-4dc8-b3b3-47d32169d8b3;3da3c651-7618-4988-8b39-cbc5279b1753;52ec3f15-0be7-4770-9ec8-2364e806d08b | d9d174d5-83da-4dc8-b3b3-47d32169d8b3 | 2026-10-14 |  |  |  | false
DeZWmIH4YkWCra9skHyTEMkABZoD | Consolidate Literature Findings & Prepare Background Summary | BQg0Or7SO0yXdcaNQTWYVMkAK1EX |  | Not started | Medium | f1d24dba-7ca3-4384-b194-da338a5a6922;d9d174d5-83da-4dc8-b3b3-47d32169d8b3;3da3c651-7618-4988-8b39-cbc5279b1753;52ec3f15-0be7-4770-9ec8-2364e806d08b | d9d174d5-83da-4dc8-b3b3-47d32169d8b3 | 2026-10-14 |  |  |  | false
TgrWE88CSk6lYB6Wgu1XGMkADp7R | Conduct Individual Literature Review for All Components | BQg0Or7SO0yXdcaNQTWYVMkAK1EX |  | Not started | Medium | d9d174d5-83da-4dc8-b3b3-47d32169d8b3;3da3c651-7618-4988-8b39-cbc5279b1753;f1d24dba-7ca3-4384-b194-da338a5a6922;52ec3f15-0be7-4770-9ec8-2364e806d08b | d9d174d5-83da-4dc8-b3b3-47d32169d8b3 | 2026-10-14 |  |  |  | false
Kz8FR7qRLEOjvi-Vbw9iockADjpG | Collect references / journals | dw0G7pnns0iv0oMJobJX4ckADVp2 |  | Not started | Medium | f1d24dba-7ca3-4384-b194-da338a5a6922;d9d174d5-83da-4dc8-b3b3-47d32169d8b3;3da3c651-7618-4988-8b39-cbc5279b1753;52ec3f15-0be7-4770-9ec8-2364e806d08b | d9d174d5-83da-4dc8-b3b3-47d32169d8b3 | 2026-10-14 |  |  |  | false
bhlgVd7xukmqbQ2GbojVB8kAEy28 | Start to write the research paper | dw0G7pnns0iv0oMJobJX4ckADVp2 |  | Not started | Medium | d9d174d5-83da-4dc8-b3b3-47d32169d8b3;3da3c651-7618-4988-8b39-cbc5279b1753;f1d24dba-7ca3-4384-b194-da338a5a6922;52ec3f15-0be7-4770-9ec8-2364e806d08b | d9d174d5-83da-4dc8-b3b3-47d32169d8b3 | 2026-10-14 |  |  |  | false
iygpwsyuik2ikzDh2EEZQ8kAHocz | Edit formatting & citations | dw0G7pnns0iv0oMJobJX4ckADVp2 |  | Not started | Medium | f1d24dba-7ca3-4384-b194-da338a5a6922;d9d174d5-83da-4dc8-b3b3-47d32169d8b3;3da3c651-7618-4988-8b39-cbc5279b1753;52ec3f15-0be7-4770-9ec8-2364e806d08b | d9d174d5-83da-4dc8-b3b3-47d32169d8b3 | 2026-10-14 |  |  |  | false
tud9R25JvU2e5goYtOz7TMkAGZre | Final proofread & submit the research paper | dw0G7pnns0iv0oMJobJX4ckADVp2 |  | Not started | Important | 52ec3f15-0be7-4770-9ec8-2364e806d08b | d9d174d5-83da-4dc8-b3b3-47d32169d8b3 | 2026-10-14 | 2026-10-23 |  |  | false
89xEbynrU0OVPNVlaQFRAckAB_Vh | Individual final thesis ready | 0Z-_xaKJb0mB34gQLtUr1MkAORi- |  | Not started | Medium | d9d174d5-83da-4dc8-b3b3-47d32169d8b3;3da3c651-7618-4988-8b39-cbc5279b1753;f1d24dba-7ca3-4384-b194-da338a5a6922;52ec3f15-0be7-4770-9ec8-2364e806d08b | d9d174d5-83da-4dc8-b3b3-47d32169d8b3 | 2026-10-14 |  |  |  | false
pOsKe4duI0iF_u_xza7hXskAHu2S | Group final thesis ready | 0Z-_xaKJb0mB34gQLtUr1MkAORi- |  | Not started | Medium | d9d174d5-83da-4dc8-b3b3-47d32169d8b3;3da3c651-7618-4988-8b39-cbc5279b1753;f1d24dba-7ca3-4384-b194-da338a5a6922;52ec3f15-0be7-4770-9ec8-2364e806d08b | d9d174d5-83da-4dc8-b3b3-47d32169d8b3 | 2026-10-14 |  |  |  | false
AjYrkQ6KHkaKQ0V_oMqzaskAEsqu | Individual final thesis submitted | 0Z-_xaKJb0mB34gQLtUr1MkAORi- |  | Not started | Medium | d9d174d5-83da-4dc8-b3b3-47d32169d8b3;3da3c651-7618-4988-8b39-cbc5279b1753;f1d24dba-7ca3-4384-b194-da338a5a6922;52ec3f15-0be7-4770-9ec8-2364e806d08b | d9d174d5-83da-4dc8-b3b3-47d32169d8b3 | 2026-10-14 | 2026-10-28 |  |  | false
JLvNuUfCkk6JuhyKsRRBTMkANrNe | Group final thesis submit | 0Z-_xaKJb0mB34gQLtUr1MkAORi- |  | Not started | Important | 52ec3f15-0be7-4770-9ec8-2364e806d08b | d9d174d5-83da-4dc8-b3b3-47d32169d8b3 | 2026-10-14 | 2026-10-28 |  |  | false
7M5tOKJtlkWEMFB9sQpBr8kAIFGy | Review logbook for completeness | _dwEpzvwP0CaiKbgK5KuE8kADNDe |  | Not started | Medium | d9d174d5-83da-4dc8-b3b3-47d32169d8b3;3da3c651-7618-4988-8b39-cbc5279b1753;f1d24dba-7ca3-4384-b194-da338a5a6922;52ec3f15-0be7-4770-9ec8-2364e806d08b | d9d174d5-83da-4dc8-b3b3-47d32169d8b3 | 2026-10-14 |  |  |  | false
2fICRyrZ2kSxZPpZqocZtckANgWj | Ensure all days are recorded | _dwEpzvwP0CaiKbgK5KuE8kADNDe |  | Not started | Medium | d9d174d5-83da-4dc8-b3b3-47d32169d8b3;3da3c651-7618-4988-8b39-cbc5279b1753;f1d24dba-7ca3-4384-b194-da338a5a6922;52ec3f15-0be7-4770-9ec8-2364e806d08b | d9d174d5-83da-4dc8-b3b3-47d32169d8b3 | 2026-10-14 |  |  |  | false
_geVoGLiuEaY2Ur5GzvdBMkACxzK | Get supervisor signature for all days | _dwEpzvwP0CaiKbgK5KuE8kADNDe |  | Not started | Medium | d9d174d5-83da-4dc8-b3b3-47d32169d8b3;3da3c651-7618-4988-8b39-cbc5279b1753;f1d24dba-7ca3-4384-b194-da338a5a6922;52ec3f15-0be7-4770-9ec8-2364e806d08b | d9d174d5-83da-4dc8-b3b3-47d32169d8b3 | 2026-10-14 |  |  |  | false
z0qvHIkOmUCEFld9bwdXBskAB2vh | Submit logbook | _dwEpzvwP0CaiKbgK5KuE8kADNDe |  | Not started | Important | d9d174d5-83da-4dc8-b3b3-47d32169d8b3;3da3c651-7618-4988-8b39-cbc5279b1753;f1d24dba-7ca3-4384-b194-da338a5a6922;52ec3f15-0be7-4770-9ec8-2364e806d08b | d9d174d5-83da-4dc8-b3b3-47d32169d8b3 | 2026-10-14 | 2026-10-21 |  |  | false
ZYDXiZ_TNE2ITz9dXa5OOskAN_0C | Prepare paper revision/publication follow-up plan | iv7-PcckD0O3eezWdHEcf8kAE_cK |  | Not started | Medium | d9d174d5-83da-4dc8-b3b3-47d32169d8b3;3da3c651-7618-4988-8b39-cbc5279b1753;f1d24dba-7ca3-4384-b194-da338a5a6922;52ec3f15-0be7-4770-9ec8-2364e806d08b | d9d174d5-83da-4dc8-b3b3-47d32169d8b3 | 2026-10-14 |  |  |  | false
031uK-lxfEa8elCOWGsMaMkAAHMR | Respond to reviewer/editor feedback if received | iv7-PcckD0O3eezWdHEcf8kAE_cK |  | Not started | Medium | d9d174d5-83da-4dc8-b3b3-47d32169d8b3;3da3c651-7618-4988-8b39-cbc5279b1753;f1d24dba-7ca3-4384-b194-da338a5a6922;52ec3f15-0be7-4770-9ec8-2364e806d08b | d9d174d5-83da-4dc8-b3b3-47d32169d8b3 | 2026-10-14 |  |  |  | false
WwbjiQ9rP0-E3kyoQHfXZckADP6O | Collect publication/acceptance evidence | iv7-PcckD0O3eezWdHEcf8kAE_cK |  | Not started | Medium | d9d174d5-83da-4dc8-b3b3-47d32169d8b3;3da3c651-7618-4988-8b39-cbc5279b1753;f1d24dba-7ca3-4384-b194-da338a5a6922;52ec3f15-0be7-4770-9ec8-2364e806d08b | d9d174d5-83da-4dc8-b3b3-47d32169d8b3 | 2026-10-14 |  |  |  | false
svcLURukxU6mrDKaKkRJB8kABbB4 | Research Paper publication evidence submission | iv7-PcckD0O3eezWdHEcf8kAE_cK |  | Not started | Medium | 52ec3f15-0be7-4770-9ec8-2364e806d08b | d9d174d5-83da-4dc8-b3b3-47d32169d8b3 | 2026-10-14 | 2026-12-01 |  |  | false

## Goals
Goal ID | Goal name | Status | Priority | Start date | Finish date | Connected tasks | Notes

## Buckets
Bucket ID | Bucket Name
m628UmO0_kmsMJLMNZTH48kAIFPo | Group Formation
PxFW6OzeK0WuClqZfCsLE8kAGmH7 | Find Research Topic & Supervisor
dZ3sRVli30e4_Shmpfbu6skAPzPW | Topic Selection & Problem Identification
QKZv960-W0iweSNTennTsskANYXx | TAF Preparation & Supervisor Approval
Efnm-wRdGUmSH4CmaLN72MkAMIP4 | Project Charter Development
nbYfgup8oUiwbO4khE_03ckAGWMj | Project Proposal Document Preparation & CDAP Submission
L3EJ3uU6C02_HrVfyiX3KMkAOYC2 | Proposal Presentation 1
ACEgOwj4Ukafa8Q-iv7ApMkAMJwI | Check List -1 Development
maWPzgr43ECIZM0OKcmkTskAD5LP | Individual Module Development
VlO41rPqGEOQ2Lw1BrY6T8kAJT8T | Progress Presentation 1 (PP1)
ZdUdBS3BA0-bW58yGGW_E8kAP2aJ | Progress Presentation 2 (PP2) – Integration & Improvement Phase
9yeUdI2tT0GsQn-2iPIr0MkAOa1I | Draft Thesis Submission
PDFlT4uHbUGrvuN36kHcjckAMWBJ | Website Submission
Dy0c50eeGk6iJt38x4lXoMkAJVRd | Final Checklist Submission
b-NzyhLKo0SN0a2KsujNc8kAJnyr | Final Presentation and Viva
_dwEpzvwP0CaiKbgK5KuE8kADNDe | Logbook Submission
BQg0Or7SO0yXdcaNQTWYVMkAK1EX | Research Paper Review & Background Study
dw0G7pnns0iv0oMJobJX4ckADVp2 | Research Paper Submission
0Z-_xaKJb0mB34gQLtUr1MkAORi- | Final Thesis Submission
iv7-PcckD0O3eezWdHEcf8kAE_cK | Research Paper publication evidence submission

## Users
User ID | User Name | Email
d9d174d5-83da-4dc8-b3b3-47d32169d8b3 | FERNANDO C.T.H.H.D it22247490 | it22247490@my.sliit.lk
3da3c651-7618-4988-8b39-cbc5279b1753 | JAYARATHNE WTDK it22071170 | it22071170@my.sliit.lk
f1d24dba-7ca3-4384-b194-da338a5a6922 | DIAS N.T.B.P it22134080 | it22134080@my.sliit.lk
52ec3f15-0be7-4770-9ec8-2364e806d08b | VIDUSHAN A A D N it22157928 | it22157928@my.sliit.lk